## README
Vector7 – Tenant Admin Pre-Configuration Template
Purpose: one-time setup data for a new tenant (layout promoter). Fill the yellow cells, run the Validation sheet, then import.
Sheets
1. Tenant Profile – name or company name, address, contact numbers and social links.
2. Additional Settings – App Settings (currency, sellable %, broker commission, budget alert, booking validity, sale completion window, MRP multiplier) and the instalment plan with due working days.
3. Notification Groups – email groups that users are tagged to.
4. Users – login users with role (Admin, Manager, Sales, Accountant) and notification groups; column H builds the CSV text for bulk import.
5. Approval Stages – approval stages and subtasks for Village, Town and City, with dependencies, durations and required documents.
6. Facility Master – facilities with Basic / Standard / Premium inclusion and unit costs for Village, Town and City.
7. Document Checklist – documents for Agri NOC, DTCP, BDO, Town, City, Gift Deed, RERA and Plot Sale, mapped to tasks.
8. Stage Checklist Map – Stage × Checklist counts and Task → Document mapping per area.
9. Validation – automatic checks; every row must show OK before import.
10. Lists – allowed values used by dropdowns.
Rules
• Do not rename sheets or column headers – the importer maps by header name.
• Yellow cells = tenant-editable. Grey cells = system/reference, keep as is.
• Add rows at the bottom of a table; keep Sino / Task ID / Facility ID unique.
• Percentages are entered as numbers (30 = 30%), not as Excel % format.
• Unit costs are indicative 2026 Tamil Nadu estimates (excl. GST) – each tenant should replace with its own rates.

## Tenant Profile
Tenant Profile
Fill the Value column. Required fields must not be blank.
Sino | Section | Field | Value | Required | Data Type | Format / Validation | Example
1 | Identity | Name or Company Name |  | Yes | Text | Max 100 characters | Sri Murugan Promoters
2 | Identity | Profile Picture |  | No | Image | PNG/JPG, square, min 512×512 px, max 2 MB (file name or URL) | logo.png
3 | Address | Address Line1 |  | Yes | Text | Door no., street – max 150 characters | 12, South Main Street
4 | Address | Address Line2 |  | No | Text | Area / landmark – max 150 characters | Near Big Temple
5 | Address | Village |  | No | Text | Village name if applicable | Vallam
6 | Address | City Or Town |  | Yes | Text | City or town name | Thanjavur
7 | Address | District |  | Yes | Text | District name | Thanjavur
8 | Address | State |  | Yes | List | Select from list | Tamil Nadu
9 | Address | Pin Code |  | Yes | Number | Exactly 6 digits | 613001
10 | Contact | Contact Number |  | Yes | Phone | 10-digit mobile, no +91 or spaces | 9876543210
11 | Contact | Alternate Contact |  | No | Phone | 10-digit mobile or landline with STD code | 04362123456
12 | Social | Insta |  | No | URL | https://www.instagram.com/<handle> | https://www.instagram.com/example
13 | Social | Face Book |  | No | URL | https://www.facebook.com/<page> | https://www.facebook.com/example
14 | Social | Website |  | No | URL | Must start with https:// | https://www.example.com
15 | Social | Youtube |  | No | URL | https://www.youtube.com/@<channel> | https://www.youtube.com/@example
16 | Social | LinkedIn |  | No | URL | https://www.linkedin.com/company/<name> | https://www.linkedin.com/company/example

## Additional Settings
Additional Settings
Importer reads columns A–F. Due Working Days applies to Instalment rows only. Description (column G) is guidance.
Sino | Type | Item | Unit | Unit Value | Due Working Days | Description
1 | App Settings | Currency | Code | INR |  | Currency for all amounts (ISO code)
2 | App Settings | Sellable SQFT % | Percentage | 55 |  | Default sellable share of total land for new projects; replaced by actual road and OSR
3 | App Settings | Broker Commission | Percentage | 0.5 |  | Commission paid to broker on sale value
4 | App Settings | Expense vs Budget Alert | Percentage | 80 |  | Alert when spend crosses this % of budget (stage, facility, project)
5 | App Settings | Booking Validity | Days | 7 |  | Booking expires if the 1st instalment is not paid within this period
6 | App Settings | Sale Completion Window | Days | 15 |  | All instalments and the sale deed must fall within this window
7 | App Settings | MRP Multiplier | Times | 3 |  | MRP per sq ft = Production cost per sq ft × this multiplier
8 | Instalment | 1st Instalment | Percentage | 30 | 0 | Due on booking day
9 | Instalment | 2nd Instalment | Percentage | 60 | 7 | Due 7 working days after booking
10 | Instalment | 3rd Instalment | Percentage | 10 | 13 | Due 13 working days after booking

## Notification Groups
Notification Groups
Email only in this release. Users are tagged to groups by Group Name.
Sino | Group Name | Type | Description | Active
1 | Management | Email | Project status changes, budget alerts, paused projects | Yes
2 | Sales Team | Email | Bookings created or expiring, instalments due or overdue | Yes
3 | Accounts | Email | Receipts, expenses, budget alerts | Yes

## Users
Users – Login Enrolment
Fill one row per login user, or copy column H (with the header in H4) and paste into Users & Roles → Bulk import. Example: Ravi Kumar, ravi@example.com, 9876543210, Manager, "Management, Sales Team".
Sino | Full Name | Email | Mobile | Role | Notification Groups | Active | full_name,email,mobile,role,notification_groups
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Approval Stages
Approval Stages – Master
One row per subtask. Default Duration is editable; Depends On lists Task IDs (comma-separated).
Sino | Area Type | Stage No | Stage | Task ID | Short Name | Subtask | Depends On | Responsible / Authority | Output / Document | Default Duration (Days) | Required Doc IDs | Doc Count | Active
1 | Village | 1 | Land Due Diligence | V1.1 | Land Records | Collect patta, chitta, A-register extract, FMB sketch |  | Owner / Surveyor | Land record set | 7 | AGR-02, AGR-04 | 2 | Yes
2 | Village | 1 | Land Due Diligence | V1.2 | EC 30 Yrs | Obtain Encumbrance Certificate (30+ years) |  | Owner / SRO | EC | 7 | AGR-05 | 1 | Yes
3 | Village | 1 | Land Due Diligence | V1.3 | Title Opinion | Collect parent documents; legal title opinion | V1.1, V1.2 | Advocate | Title opinion | 10 | AGR-06, DTC-04 | 2 | Yes
4 | Village | 1 | Land Due Diligence | V1.4 | Legal Risk Check | Verify no poramboke, land-ceiling, litigation or acquisition issues | V1.3 | Advocate / Taluk office | Clearance note | 7 |  | 0 | Yes
5 | Village | 1 | Land Due Diligence | V1.5 | Boundary Survey | Field survey and boundary fixing with neighbours | V1.1 | Licensed Surveyor | Boundary sketch | 5 |  | 0 | Yes
6 | Village | 2 | Classification & Feasibility | V2.1 | Dry/Wet Check | Confirm dry (punjai) vs wet (nanjai) classification | V1.1 | Owner / VAO | Classification note | 3 | AGR-03, AGR-08, AGR-09 | 3 | Yes
7 | Village | 2 | Classification & Feasibility | V2.2 | Planning Status | Confirm land is in a non-planning area | V1.1 | DTCP (District / Regional office) | Planning status | 5 |  | 0 | Yes
8 | Village | 2 | Classification & Feasibility | V2.3 | Buffer Check | Check buffers: NH (40 m residential), water bodies, railway, airport | V1.5 | Surveyor / Planner | Buffer check | 3 |  | 0 | Yes
9 | Village | 2 | Classification & Feasibility | V2.4 | Go/No-Go | Go / No-Go feasibility decision | V1.4, V2.1, V2.2, V2.3 | Owner / Developer | Decision | 2 |  | 0 | Yes
10 | Village | 3 | Change of Land Use (CLU) | V3.1 | CLU Application | Prepare CLU application (TN CLU Rules 2017, as amended by G.O. 149 / 2026) | V2.4 | Owner / Consultant | CLU application | 5 | AGR-01, AGR-12, AGR-13, AGR-14 | 4 | Yes
11 | Village | 3 | Change of Land Use (CLU) | V3.2 | CLU Submit | Submit CLU application online | V3.1 | Owner / Consultant | Acknowledgement | 1 |  | 0 | Yes
12 | Village | 3 | Change of Land Use (CLU) | V3.3 | CLU Inspection | Field inspection and report | V3.2 | DTCP (District / Regional office) / Revenue | Inspection report | 30 | AGR-10 | 1 | Yes
13 | Village | 3 | Change of Land Use (CLU) | V3.4 | CLU Fees | Pay conversion charges | V3.3 | Owner | Challan | 3 | AGR-15 | 1 | Yes
14 | Village | 3 | Change of Land Use (CLU) | V3.5 | CLU Order | Receive CLU order | V3.4 | DTCP (District / Regional office) | CLU order | 15 | AGR-16 | 1 | Yes
15 | Village | 4 | Layout Design | V4.1 | Engage Consultants | Engage licensed surveyor and registered architect / planner | V2.4 | Owner | Engagement | 5 |  | 0 | Yes
16 | Village | 4 | Layout Design | V4.2 | Topo Survey | Topographic survey and levels | V4.1, V1.5 | Licensed Surveyor | Topo drawing | 7 | DTC-06 | 1 | Yes
17 | Village | 4 | Layout Design | V4.3 | Draft Layout | Draft layout per TNCDBR 2019 (roads, OSR, public-purpose area, plots) | V4.2 | Architect / Planner | Draft layout | 10 | AGR-07, DTC-07, DTC-08 | 3 | Yes
18 | Village | 4 | Layout Design | V4.4 | Finalise Drawings | Internal review and finalise drawings | V4.3 | Owner / Architect | Final drawings | 5 |  | 0 | Yes
19 | Village | 5 | NOCs | V5.1 | NOC Checklist | Identify NOCs required for the site | V4.3 | Planner | NOC checklist | 2 | DTC-11 | 1 | Yes
20 | Village | 5 | NOCs | V5.2 | WRD NOC | WRD / PWD NOC (if near tank, river, channel) | V5.1 | Water Resources Dept | NOC | 30 | AGR-11 | 1 | Yes
21 | Village | 5 | NOCs | V5.3 | Highways NOC | Highways NOC (if abutting NH / SH) | V5.1 | NHAI / State Highways | NOC | 30 |  | 0 | Yes
22 | Village | 5 | NOCs | V5.4 | Local Body NOC | No-objection / resolution from Village Panchayat / Panchayat Union | V5.1 | Village Panchayat / Panchayat Union | Resolution / NOC | 15 | BDO-02 | 1 | Yes
23 | Village | 5 | NOCs | V5.5 | Access Road Cert | Access-road certificate (Annexure-XVII, from road register) | V5.1 | BDO, Panchayat Union | Annexure-XVII certificate | 15 | DTC-09, BDO-03 | 2 | Yes
24 | Village | 6 | Layout Application | V6.1 | Portal Registration | Register on TN online planning permission portal |  | Owner / Consultant | Login | 1 |  | 0 | Yes
25 | Village | 6 | Layout Application | V6.2 | Submit Application | Upload documents, CLU/zone order, drawings, NOCs | V3.5, V4.4, V5.2, V5.3, V5.4, V5.5, V6.1 | Owner / Consultant | Application ID | 2 | DTC-01, DTC-02, DTC-03, DTC-05, DTC-10, DTC-12, BDO-01 | 7 | Yes
26 | Village | 6 | Layout Application | V6.3 | Scrutiny Fees | Pay scrutiny / processing fees | V6.2 | Owner | Receipt | 1 | DTC-13 | 1 | Yes
27 | Village | 6 | Layout Application | V6.4 | BDO Forwarding | BDO scrutiny and forwarding to DTCP for technical sanction | V6.3 | BDO, Panchayat Union | Forwarding letter | 15 | BDO-04 | 1 | Yes
28 | Village | 7 | Scrutiny | V7.1 | Site Inspection | Site inspection by authority | V6.4 | DTCP (District / Regional office) | Inspection report | 15 |  | 0 | Yes
29 | Village | 7 | Scrutiny | V7.2 | Revise Drawings | Respond to objections; submit revised drawings | V7.1 | Architect / Planner | Revised drawings | 10 | DTC-14 | 1 | Yes
30 | Village | 7 | Scrutiny | V7.3 | Scrutiny Complete | Technical scrutiny complete | V7.2 | DTCP (District / Regional office) | Scrutiny note | 15 |  | 0 | Yes
31 | Village | 8 | Charges | V8.1 | Demand Notice | Receive demand notice | V7.3 | DTCP (District / Regional office) / Village Panchayat / Panchayat Union | Demand notice | 5 |  | 0 | Yes
32 | Village | 8 | Charges | V8.2 | Pay Charges | Pay development, infrastructure / amenity and OSR charges | V8.1 | Owner | Challans | 5 | DTC-15, BDO-06 | 2 | Yes
33 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Register gift deed of roads and OSR to Village Panchayat / Panchayat Union (accepted by BDO) | V8.2 | Owner / SRO | Registered gift deed | 7 | DTC-16, BDO-07, BDO-08, GFT-01, GFT-02, GFT-03, GFT-04, GFT-05, GFT-06, GFT-07, GFT-08, GFT-09, GFT-10 | 13 | Yes
34 | Village | 9 | Handover (Gift Deed) | V9.2 | DTCP Sanction | Receive DTCP technical sanction with LP number | V9.1 | DTCP (District / Regional office) | Approval / LP number | 15 | DTC-17, BDO-05 | 2 | Yes
35 | Village | 9 | Handover (Gift Deed) | V9.3 | BDO Final Approval | Final layout approval issued by BDO (Executive Authority) under TN Panchayat Building Rules | V9.2 | BDO, Panchayat Union | Layout approval order | 15 | BDO-09 | 1 | Yes
36 | Village | 10 | Development Works | V10.1 | Roads | Form roads as per approved widths | V9.3 | Contractor | Roads | 45 |  | 0 | Yes
37 | Village | 10 | Development Works | V10.2 | Drains | Storm-water drains / culverts | V9.3 | Contractor | Drains | 30 |  | 0 | Yes
38 | Village | 10 | Development Works | V10.3 | Streetlights & EB | Streetlights and EB line extension | V9.3 | Contractor / TANGEDCO | EB lines | 30 |  | 0 | Yes
39 | Village | 10 | Development Works | V10.4 | Water Supply | Water supply arrangement | V9.3 | Contractor / Village Panchayat / Panchayat Union | Water supply | 30 |  | 0 | Yes
40 | Village | 10 | Development Works | V10.5 | Plot Stones | Plot demarcation stones and OSR fencing | V9.3 | Surveyor / Contractor | Stones & fencing | 10 |  | 0 | Yes
41 | Village | 10 | Development Works | V10.6 | Completion Check | Completion inspection by local body | V10.1, V10.2, V10.3, V10.4, V10.5 | Village Panchayat / Panchayat Union | Inspection report | 15 | BDO-10 | 1 | Yes
42 | Village | 11 | Final Approval & Release | V11.1 | Plot Release | Release of plots for registration | V10.6 | BDO, Panchayat Union | Release letter | 15 | BDO-11, SAL-02 | 2 | Yes
43 | Village | 11 | Final Approval & Release | V11.2 | LP Verification | Verify LP number on onlineppa.tn.gov.in | V11.1 | Owner | Verification | 1 |  | 0 | Yes
44 | Village | 12 | RERA | V12.1 | RERA Check | Check TNRERA threshold (>500 sq m or >8 plots) | V9.3 | Consultant | Applicability | 1 | RER-01 | 1 | Yes
45 | Village | 12 | RERA | V12.2 | RERA Registration | Register project with TNRERA | V12.1 | TNRERA | RERA number | 30 | RER-02, RER-03, RER-04, RER-05, RER-06, RER-07, RER-08, RER-09, RER-10, RER-11, RER-12, RER-13, RER-14, RER-15, SAL-03 | 15 | Yes
46 | Village | 13 | Sub-division & Sale | V13.1 | Sub-division | Survey sub-division for individual plots | V11.1 | Taluk / Survey dept | Sub-division | 30 | SAL-05 | 1 | Yes
47 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Marketing and bookings | V11.1, V12.2 | Developer | Bookings | 30 | SAL-01, SAL-04, SAL-06, SAL-07, SAL-08, SAL-09, SAL-10 | 7 | Yes
48 | Village | 13 | Sub-division & Sale | V13.3 | Sale Deeds | Register sale deeds | V13.1, V13.2 | SRO | Sale deeds | 15 | SAL-11, SAL-12, SAL-13, SAL-14, SAL-15 | 5 | Yes
49 | Village | 13 | Sub-division & Sale | V13.4 | Patta Transfer | Patta transfer to buyers | V13.3 | Taluk office | Buyer pattas | 30 | SAL-16 | 1 | Yes
50 | Town | 1 | Land Due Diligence | T1.1 | Land Records | Collect patta, chitta, A-register extract, FMB sketch |  | Owner / Surveyor | Land record set | 7 | AGR-02, AGR-04 | 2 | Yes
51 | Town | 1 | Land Due Diligence | T1.2 | EC 30 Yrs | Obtain Encumbrance Certificate (30+ years) |  | Owner / SRO | EC | 7 | AGR-05 | 1 | Yes
52 | Town | 1 | Land Due Diligence | T1.3 | Title Opinion | Collect parent documents; legal title opinion | T1.1, T1.2 | Advocate | Title opinion | 10 | AGR-06, DTC-04 | 2 | Yes
53 | Town | 1 | Land Due Diligence | T1.4 | Legal Risk Check | Verify no poramboke, land-ceiling, litigation or acquisition issues | T1.3 | Advocate / Taluk office | Clearance note | 7 |  | 0 | Yes
54 | Town | 1 | Land Due Diligence | T1.5 | Boundary Survey | Field survey and boundary fixing with neighbours | T1.1 | Licensed Surveyor | Boundary sketch | 5 |  | 0 | Yes
55 | Town | 2 | Classification & Feasibility | T2.1 | Dry/Wet Check | Confirm dry (punjai) vs wet (nanjai) classification | T1.1 | Owner / VAO | Classification note | 3 | AGR-03, AGR-08, AGR-09 | 3 | Yes
56 | Town | 2 | Classification & Feasibility | T2.2 | Zone Check | Check Master Plan / LPA zoning of survey number | T1.1 | Local Planning Authority / DTCP (District / Regional office) | Zone extract | 7 | TWN-01 | 1 | Yes
57 | Town | 2 | Classification & Feasibility | T2.3 | Buffer Check | Check buffers: NH (40 m residential), water bodies, railway, airport | T1.5 | Surveyor / Planner | Buffer check | 3 |  | 0 | Yes
58 | Town | 2 | Classification & Feasibility | T2.4 | Go/No-Go | Go / No-Go feasibility decision | T1.4, T2.1, T2.2, T2.3 | Owner / Developer | Decision | 2 |  | 0 | Yes
59 | Town | 3 | Zone Conversion / CLU | T3.1 | Zone Application | If already residential zone: obtain zone certificate; else prepare reclassification application | T2.4 | Owner / Planner | Application | 7 | AGR-01, AGR-12, AGR-13, AGR-14 | 4 | Yes
60 | Town | 3 | Zone Conversion / CLU | T3.2 | Zone Submit | Submit reclassification to LPA / DTCP | T3.1 | Owner / Planner | Acknowledgement | 1 |  | 0 | Yes
61 | Town | 3 | Zone Conversion / CLU | T3.3 | Public Notice | Scrutiny, site inspection and paper publication for public objections | T3.2 | LPA / DTCP (District / Regional office) | Notice | 45 | AGR-10 | 1 | Yes
62 | Town | 3 | Zone Conversion / CLU | T3.4 | Objection Hearing | Hearing of objections; recommendation to Government | T3.3 | LPA / DTCP (District / Regional office) | Recommendation | 30 |  | 0 | Yes
63 | Town | 3 | Zone Conversion / CLU | T3.5 | Zone Fees | Pay reclassification charges | T3.4 | Owner | Challan | 3 | AGR-15 | 1 | Yes
64 | Town | 3 | Zone Conversion / CLU | T3.6 | Zone Order | Receive Government / authority reclassification order | T3.5 | Housing & Urban Development Dept | Reclassification order | 30 | AGR-16, TWN-02 | 2 | Yes
65 | Town | 4 | Layout Design | T4.1 | Engage Consultants | Engage licensed surveyor and registered architect / planner | T2.4 | Owner | Engagement | 5 |  | 0 | Yes
66 | Town | 4 | Layout Design | T4.2 | Topo Survey | Topographic survey and levels | T4.1, T1.5 | Licensed Surveyor | Topo drawing | 7 | DTC-06 | 1 | Yes
67 | Town | 4 | Layout Design | T4.3 | Draft Layout | Draft layout per TNCDBR 2019 (roads, OSR, public-purpose area, plots) | T4.2 | Architect / Planner | Draft layout | 10 | AGR-07, DTC-07, DTC-08 | 3 | Yes
68 | Town | 4 | Layout Design | T4.4 | Finalise Drawings | Internal review and finalise drawings | T4.3 | Owner / Architect | Final drawings | 5 |  | 0 | Yes
69 | Town | 5 | NOCs | T5.1 | NOC Checklist | Identify NOCs required for the site | T4.3 | Planner | NOC checklist | 2 | DTC-11 | 1 | Yes
70 | Town | 5 | NOCs | T5.2 | WRD NOC | WRD / PWD NOC (if near tank, river, channel) | T5.1 | Water Resources Dept | NOC | 30 | AGR-11 | 1 | Yes
71 | Town | 5 | NOCs | T5.3 | Highways NOC | Highways NOC (if abutting NH / SH) | T5.1 | NHAI / State Highways | NOC | 30 |  | 0 | Yes
72 | Town | 5 | NOCs | T5.4 | Local Body NOC | No-objection / resolution from Town Panchayat / Municipality | T5.1 | Town Panchayat / Municipality | Resolution / NOC | 15 | TWN-07 | 1 | Yes
73 | Town | 5 | NOCs | T5.5 | Access Road Cert | Access-road certificate (Annexure-XVII, from road register) | T5.1 | Executive Officer / Municipal Commissioner | Annexure-XVII certificate | 15 | DTC-09, TWN-04 | 2 | Yes
74 | Town | 5 | NOCs | T5.6 | Water/Drain Feasibility | Water supply and drainage feasibility | T5.1 | Town Panchayat / Municipality | Feasibility letter | 15 | TWN-05 | 1 | Yes
75 | Town | 6 | Layout Application | T6.1 | Portal Registration | Register on TN online planning permission portal |  | Owner / Consultant | Login | 1 |  | 0 | Yes
76 | Town | 6 | Layout Application | T6.2 | Submit Application | Upload documents, CLU/zone order, drawings, NOCs | T3.6, T4.4, T5.2, T5.3, T5.4, T5.5, T5.6, T6.1 | Owner / Consultant | Application ID | 2 | DTC-01, DTC-02, DTC-03, DTC-05, DTC-10, DTC-12, TWN-03, TWN-06 | 8 | Yes
77 | Town | 6 | Layout Application | T6.3 | Scrutiny Fees | Pay scrutiny / processing fees | T6.2 | Owner | Receipt | 1 | DTC-13 | 1 | Yes
78 | Town | 7 | Scrutiny | T7.1 | Site Inspection | Site inspection by authority | T6.3 | DTCP (District / Regional office) | Inspection report | 20 |  | 0 | Yes
79 | Town | 7 | Scrutiny | T7.2 | Revise Drawings | Respond to objections; submit revised drawings | T7.1 | Architect / Planner | Revised drawings | 10 | DTC-14 | 1 | Yes
80 | Town | 7 | Scrutiny | T7.3 | Scrutiny Complete | Technical scrutiny complete | T7.2 | DTCP (District / Regional office) | Scrutiny note | 15 |  | 0 | Yes
81 | Town | 8 | Charges | T8.1 | Demand Notice | Receive demand notice | T7.3 | DTCP (District / Regional office) / Town Panchayat / Municipality | Demand notice | 5 |  | 0 | Yes
82 | Town | 8 | Charges | T8.2 | Pay Charges | Pay development, infrastructure / amenity and OSR charges | T8.1 | Owner | Challans | 5 | DTC-15, TWN-08 | 2 | Yes
83 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Register gift deed of roads and OSR to Town Panchayat / Municipality | T8.2 | Owner / SRO | Registered gift deed | 7 | DTC-16, TWN-09, GFT-01, GFT-02, GFT-03, GFT-04, GFT-05, GFT-06, GFT-07, GFT-08, GFT-09, GFT-10 | 12 | Yes
84 | Town | 9 | Handover (Gift Deed) | T9.2 | Layout Approval | Receive approval with LP number (conditions listed) | T9.1 | DTCP (District / Regional office) | Approval / LP number | 15 | DTC-17 | 1 | Yes
85 | Town | 10 | Development Works | T10.1 | Roads | Form roads as per approved widths | T9.2 | Contractor | Roads | 45 |  | 0 | Yes
86 | Town | 10 | Development Works | T10.2 | Drains | Storm-water drains / culverts | T9.2 | Contractor | Drains | 30 |  | 0 | Yes
87 | Town | 10 | Development Works | T10.3 | Streetlights & EB | Streetlights and EB line extension | T9.2 | Contractor / TANGEDCO | EB lines | 30 |  | 0 | Yes
88 | Town | 10 | Development Works | T10.4 | Water Supply | Water supply arrangement | T9.2 | Contractor / Town Panchayat / Municipality | Water supply | 30 |  | 0 | Yes
89 | Town | 10 | Development Works | T10.5 | Plot Stones | Plot demarcation stones and OSR fencing | T9.2 | Surveyor / Contractor | Stones & fencing | 10 |  | 0 | Yes
90 | Town | 10 | Development Works | T10.6 | Completion Check | Completion inspection by local body | T10.1, T10.2, T10.3, T10.4, T10.5 | Town Panchayat / Municipality | Inspection report | 15 | TWN-10 | 1 | Yes
91 | Town | 11 | Final Approval & Release | T11.1 | Plot Release | Release of plots for registration | T10.6 | Town Panchayat / Municipality / DTCP (District / Regional office) | Release letter | 15 | TWN-11, SAL-02 | 2 | Yes
92 | Town | 11 | Final Approval & Release | T11.2 | LP Verification | Verify LP number on onlineppa.tn.gov.in | T11.1 | Owner | Verification | 1 |  | 0 | Yes
93 | Town | 12 | RERA | T12.1 | RERA Check | Check TNRERA threshold (>500 sq m or >8 plots) | T9.2 | Consultant | Applicability | 1 | RER-01 | 1 | Yes
94 | Town | 12 | RERA | T12.2 | RERA Registration | Register project with TNRERA | T12.1 | TNRERA | RERA number | 30 | RER-02, RER-03, RER-04, RER-05, RER-06, RER-07, RER-08, RER-09, RER-10, RER-11, RER-12, RER-13, RER-14, RER-15, SAL-03 | 15 | Yes
95 | Town | 13 | Sub-division & Sale | T13.1 | Sub-division | Survey sub-division for individual plots | T11.1 | Taluk / Survey dept | Sub-division | 30 | SAL-05 | 1 | Yes
96 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Marketing and bookings | T11.1, T12.2 | Developer | Bookings | 30 | SAL-01, SAL-04, SAL-06, SAL-07, SAL-08, SAL-09, SAL-10 | 7 | Yes
97 | Town | 13 | Sub-division & Sale | T13.3 | Sale Deeds | Register sale deeds | T13.1, T13.2 | SRO | Sale deeds | 15 | SAL-11, SAL-12, SAL-13, SAL-14, SAL-15 | 5 | Yes
98 | Town | 13 | Sub-division & Sale | T13.4 | Patta Transfer | Patta transfer to buyers | T13.3 | Taluk office | Buyer pattas | 30 | SAL-16 | 1 | Yes
99 | City | 1 | Land Due Diligence | C1.1 | Land Records | Collect patta, chitta, A-register extract, FMB sketch |  | Owner / Surveyor | Land record set | 7 | AGR-02, AGR-04 | 2 | Yes
100 | City | 1 | Land Due Diligence | C1.2 | EC 30 Yrs | Obtain Encumbrance Certificate (30+ years) |  | Owner / SRO | EC | 7 | AGR-05 | 1 | Yes
101 | City | 1 | Land Due Diligence | C1.3 | Title Opinion | Collect parent documents; legal title opinion | C1.1, C1.2 | Advocate | Title opinion | 10 | AGR-06, DTC-04 | 2 | Yes
102 | City | 1 | Land Due Diligence | C1.4 | Legal Risk Check | Verify no poramboke, land-ceiling, litigation or acquisition issues | C1.3 | Advocate / Taluk office | Clearance note | 7 |  | 0 | Yes
103 | City | 1 | Land Due Diligence | C1.5 | Boundary Survey | Field survey and boundary fixing with neighbours | C1.1 | Licensed Surveyor | Boundary sketch | 5 |  | 0 | Yes
104 | City | 2 | Classification & Feasibility | C2.1 | Dry/Wet Check | Confirm dry (punjai) vs wet (nanjai) classification | C1.1 | Owner / VAO | Classification note | 3 | AGR-03, AGR-08, AGR-09 | 3 | Yes
105 | City | 2 | Classification & Feasibility | C2.2 | Zone Check | Check Master Plan / LPA zoning of survey number | C1.1 | Local Planning Authority / DTCP Regional office (CMDA if inside Chennai Metro Area) | Zone extract | 7 | CTY-01 | 1 | Yes
106 | City | 2 | Classification & Feasibility | C2.3 | Buffer Check | Check buffers: NH (40 m residential), water bodies, railway, airport | C1.5 | Surveyor / Planner | Buffer check | 3 |  | 0 | Yes
107 | City | 2 | Classification & Feasibility | C2.4 | Go/No-Go | Go / No-Go feasibility decision | C1.4, C2.1, C2.2, C2.3 | Owner / Developer | Decision | 2 |  | 0 | Yes
108 | City | 3 | Zone Conversion / CLU | C3.1 | Zone Application | If already residential zone: obtain zone certificate; else prepare reclassification application | C2.4 | Owner / Planner | Application | 7 | AGR-01, AGR-12, AGR-13, AGR-14 | 4 | Yes
109 | City | 3 | Zone Conversion / CLU | C3.2 | Zone Submit | Submit reclassification to LPA / DTCP / CMDA | C3.1 | Owner / Planner | Acknowledgement | 1 |  | 0 | Yes
110 | City | 3 | Zone Conversion / CLU | C3.3 | Public Notice | Scrutiny, site inspection and paper publication for public objections | C3.2 | LPA / DTCP Regional office (CMDA if inside Chennai Metro Area) | Notice | 60 | AGR-10 | 1 | Yes
111 | City | 3 | Zone Conversion / CLU | C3.4 | Objection Hearing | Hearing of objections; recommendation to Government | C3.3 | LPA / DTCP Regional office (CMDA if inside Chennai Metro Area) | Recommendation | 45 |  | 0 | Yes
112 | City | 3 | Zone Conversion / CLU | C3.5 | Zone Fees | Pay reclassification charges | C3.4 | Owner | Challan | 3 | AGR-15 | 1 | Yes
113 | City | 3 | Zone Conversion / CLU | C3.6 | Zone Order | Receive Government / authority reclassification order | C3.5 | Housing & Urban Development Dept | Reclassification order | 45 | AGR-16, CTY-02 | 2 | Yes
114 | City | 4 | Layout Design | C4.1 | Engage Consultants | Engage licensed surveyor and registered architect / planner | C2.4 | Owner | Engagement | 5 |  | 0 | Yes
115 | City | 4 | Layout Design | C4.2 | Topo Survey | Topographic survey and levels | C4.1, C1.5 | Licensed Surveyor | Topo drawing | 7 | DTC-06 | 1 | Yes
116 | City | 4 | Layout Design | C4.3 | Draft Layout | Draft layout per TNCDBR 2019 (roads, OSR, public-purpose area, plots) | C4.2 | Architect / Planner | Draft layout | 10 | AGR-07, DTC-07, DTC-08 | 3 | Yes
117 | City | 4 | Layout Design | C4.4 | Finalise Drawings | Internal review and finalise drawings | C4.3 | Owner / Architect | Final drawings | 5 |  | 0 | Yes
118 | City | 5 | NOCs | C5.1 | NOC Checklist | Identify NOCs required for the site | C4.3 | Planner | NOC checklist | 2 | DTC-11 | 1 | Yes
119 | City | 5 | NOCs | C5.2 | WRD NOC | WRD / PWD NOC (if near tank, river, channel) | C5.1 | Water Resources Dept | NOC | 30 | AGR-11 | 1 | Yes
120 | City | 5 | NOCs | C5.3 | Highways NOC | Highways NOC (if abutting NH / SH) | C5.1 | NHAI / State Highways | NOC | 30 | CTY-07 | 1 | Yes
121 | City | 5 | NOCs | C5.4 | Local Body NOC | No-objection / resolution from City Corporation | C5.1 | City Corporation | Resolution / NOC | 15 |  | 0 | Yes
122 | City | 5 | NOCs | C5.5 | Access Road Cert | Access-road certificate (Annexure-XVII, from road register) | C5.1 | Corporation Commissioner | Annexure-XVII certificate | 15 | DTC-09, CTY-04 | 2 | Yes
123 | City | 5 | NOCs | C5.6 | Water/Drain Feasibility | Water supply and drainage feasibility | C5.1 | City Corporation | Feasibility letter | 15 | CTY-06 | 1 | Yes
124 | City | 5 | NOCs | C5.7 | Other NOCs | Airport / Railway / Fire & other NOCs as applicable | C5.1 | AAI / Railways / others | NOCs | 45 | CTY-08, CTY-09, CTY-10 | 3 | Yes
125 | City | 6 | Layout Application | C6.1 | Portal Registration | Register on TN online planning permission portal |  | Owner / Consultant | Login | 1 |  | 0 | Yes
126 | City | 6 | Layout Application | C6.2 | Submit Application | Upload documents, CLU/zone order, drawings, NOCs | C3.6, C4.4, C5.2, C5.3, C5.4, C5.5, C5.6, C5.7, C6.1 | Owner / Consultant | Application ID | 2 | DTC-01, DTC-02, DTC-03, DTC-05, DTC-10, DTC-12, CTY-03, CTY-05 | 8 | Yes
127 | City | 6 | Layout Application | C6.3 | Scrutiny Fees | Pay scrutiny / processing fees | C6.2 | Owner | Receipt | 1 | DTC-13 | 1 | Yes
128 | City | 7 | Scrutiny | C7.1 | Site Inspection | Site inspection by authority | C6.3 | DTCP Regional office (CMDA if inside Chennai Metro Area) | Inspection report | 20 |  | 0 | Yes
129 | City | 7 | Scrutiny | C7.2 | Revise Drawings | Respond to objections; submit revised drawings | C7.1 | Architect / Planner | Revised drawings | 10 | DTC-14 | 1 | Yes
130 | City | 7 | Scrutiny | C7.3 | Scrutiny Complete | Technical scrutiny complete | C7.2 | DTCP Regional office (CMDA if inside Chennai Metro Area) | Scrutiny note | 20 |  | 0 | Yes
131 | City | 8 | Charges | C8.1 | Demand Notice | Receive demand notice | C7.3 | DTCP Regional office (CMDA if inside Chennai Metro Area) / City Corporation | Demand notice | 5 |  | 0 | Yes
132 | City | 8 | Charges | C8.2 | Pay Charges | Pay development, infrastructure / amenity and OSR charges | C8.1 | Owner | Challans | 5 | DTC-15, CTY-11 | 2 | Yes
133 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Register gift deed of roads and OSR to City Corporation | C8.2 | Owner / SRO | Registered gift deed | 7 | DTC-16, CTY-12, GFT-01, GFT-02, GFT-03, GFT-04, GFT-05, GFT-06, GFT-07, GFT-08, GFT-09, GFT-10 | 12 | Yes
134 | City | 9 | Handover (Gift Deed) | C9.2 | Layout Approval | Receive approval with LP number (conditions listed) | C9.1 | DTCP Regional office (CMDA if inside Chennai Metro Area) | Approval / LP number | 15 | DTC-17 | 1 | Yes
135 | City | 10 | Development Works | C10.1 | Roads | Form roads as per approved widths | C9.2 | Contractor | Roads | 45 |  | 0 | Yes
136 | City | 10 | Development Works | C10.2 | Drains | Storm-water drains / culverts | C9.2 | Contractor | Drains | 30 |  | 0 | Yes
137 | City | 10 | Development Works | C10.3 | Streetlights & EB | Streetlights and EB line extension | C9.2 | Contractor / TANGEDCO | EB lines | 30 |  | 0 | Yes
138 | City | 10 | Development Works | C10.4 | Water Supply | Water supply arrangement | C9.2 | Contractor / City Corporation | Water supply | 30 |  | 0 | Yes
139 | City | 10 | Development Works | C10.5 | Plot Stones | Plot demarcation stones and OSR fencing | C9.2 | Surveyor / Contractor | Stones & fencing | 10 |  | 0 | Yes
140 | City | 10 | Development Works | C10.6 | Completion Check | Completion inspection by local body | C10.1, C10.2, C10.3, C10.4, C10.5 | City Corporation | Inspection report | 15 | CTY-13 | 1 | Yes
141 | City | 11 | Final Approval & Release | C11.1 | Plot Release | Release of plots for registration | C10.6 | City Corporation / DTCP Regional office (CMDA if inside Chennai Metro Area) | Release letter | 15 | CTY-14, SAL-02 | 2 | Yes
142 | City | 11 | Final Approval & Release | C11.2 | LP Verification | Verify LP number on onlineppa.tn.gov.in | C11.1 | Owner | Verification | 1 |  | 0 | Yes
143 | City | 12 | RERA | C12.1 | RERA Check | Check TNRERA threshold (>500 sq m or >8 plots) | C9.2 | Consultant | Applicability | 1 | RER-01 | 1 | Yes
144 | City | 12 | RERA | C12.2 | RERA Registration | Register project with TNRERA | C12.1 | TNRERA | RERA number | 30 | RER-02, RER-03, RER-04, RER-05, RER-06, RER-07, RER-08, RER-09, RER-10, RER-11, RER-12, RER-13, RER-14, RER-15, SAL-03 | 15 | Yes
145 | City | 13 | Sub-division & Sale | C13.1 | Sub-division | Survey sub-division for individual plots | C11.1 | Taluk / Survey dept | Sub-division | 30 | SAL-05 | 1 | Yes
146 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Marketing and bookings | C11.1, C12.2 | Developer | Bookings | 30 | SAL-01, SAL-04, SAL-06, SAL-07, SAL-08, SAL-09, SAL-10 | 7 | Yes
147 | City | 13 | Sub-division & Sale | C13.3 | Sale Deeds | Register sale deeds | C13.1, C13.2 | SRO | Sale deeds | 15 | SAL-11, SAL-12, SAL-13, SAL-14, SAL-15 | 5 | Yes
148 | City | 13 | Sub-division & Sale | C13.4 | Patta Transfer | Patta transfer to buyers | C13.3 | Taluk office | Buyer pattas | 30 | SAL-16 | 1 | Yes

## Facility Master
Facility Master
Tier flags: Y = included · Opt = optional (not costed) · - = not included. Unit costs in ₹, excl. GST.
Sino | Facility ID | Category | Facility | Specification | Unit | Basic | Standard | Premium | Statutory | Village Unit Cost (₹) | Town Unit Cost (₹) | City Unit Cost (₹) | Active
1 | F01 | Roads | Gravel / WBM road | Compacted gravel with WBM layers | sq m | Y | - | - | Yes | 450 | 495 | 562 | Yes
2 | F02 | Roads | Bituminous (BT) road | WMM base + 50 mm BT surface | sq m | - | Y | - | Yes | 900 | 990 | 1125 | Yes
3 | F03 | Roads | Cement concrete (CC) road | M30 concrete, 200 mm, on GSB base | sq m | - | - | Y | Yes | 1600 | 1760 | 2000 | Yes
4 | F04 | Roads | Kerb stones | Precast kerb both sides | running m | - | Y | Y | No | 450 | 495 | 562 | Yes
5 | F05 | Roads | Footpath with paver blocks | 1.2 m wide, both sides | running m | - | - | Y | No | 1400 | 1540 | 1750 | Yes
6 | F06 | Drainage | Open PCC / brick drain | Lined open drain, both sides | running m | Y | - | - | Yes | 1200 | 1320 | 1500 | Yes
7 | F07 | Drainage | Covered RCC drain | RCC drain with cover slabs, both sides | running m | - | Y | Y | Yes | 3500 | 3850 | 4375 | Yes
8 | F08 | Drainage | Road crossing culverts | RCC pipe / box culvert | nos | Y | Y | Y | Yes | 60000 | 66000 | 75000 | Yes
9 | F09 | Drainage | Underground sewer line (UGD) | PVC/SW pipe with manholes | running m | - | - | Y | No | 4500 | 4950 | 5625 | Yes
10 | F10 | Drainage | Sewage treatment plant (package) | Packaged STP | KLD | - | - | Y | No | 80000 | 88000 | 100000 | Yes
11 | F11 | Water | Borewell with submersible pump | Common source | nos | Y | Y | Y | No | 250000 | 275000 | 312500 | Yes
12 | F12 | Water | Overhead tank (OHT) | RCC / sintex elevated storage | litres | - | Y | Y | No | 20 | 22 | 25 | Yes
13 | F13 | Water | Distribution pipeline | HDPE / PVC 90–110 mm | running m | Y | Y | Y | No | 650 | 715 | 812 | Yes
14 | F14 | Water | House service connection stub | Valve + stub per plot | plots | - | Y | Y | No | 3500 | 3850 | 4375 | Yes
15 | F15 | Water | Common rainwater harvesting pits | Recharge pits in OSR / roads | nos | Y | Y | Y | Yes | 35000 | 38500 | 43750 | Yes
16 | F16 | Electrical | LT line (poles + conductor) | Overhead LT distribution | running m | Y | Y | - | Yes | 1200 | 1320 | 1500 | Yes
17 | F17 | Electrical | Underground LT cabling | Armoured cable with feeder pillars | running m | - | - | Y | No | 2500 | 2750 | 3125 | Yes
18 | F18 | Electrical | Distribution transformer | 250 kVA incl. installation | nos | Y | Y | Y | No | 900000 | 990000 | 1125000 | Yes
19 | F19 | Electrical | Streetlight – LED on GI pole | 7–9 m pole, 60 W LED | nos | Y | Y | - | Yes | 22000 | 24200 | 27500 | Yes
20 | F20 | Electrical | Decorative / solar streetlight | Decorative pole or solar LED | nos | - | - | Y | Yes | 45000 | 49500 | 56250 | Yes
21 | F21 | Boundary & Entry | Plot demarcation stones | Granite stones at plot corners | nos | Y | Y | Y | Yes | 600 | 660 | 750 | Yes
22 | F22 | Boundary & Entry | Chain-link perimeter fence | 1.5 m with angle posts | running m | Y | - | - | No | 1200 | 1320 | 1500 | Yes
23 | F23 | Boundary & Entry | Compound wall (perimeter) | Brick/block wall 1.8 m | running m | - | Y | Y | No | 5500 | 6050 | 6875 | Yes
24 | F24 | Boundary & Entry | Entrance name board | Steel / ACP board | nos | Y | - | - | No | 40000 | 44000 | 50000 | Yes
25 | F25 | Boundary & Entry | Entrance arch | RCC arch with signage | nos | - | Y | - | No | 600000 | 660000 | 750000 | Yes
26 | F26 | Boundary & Entry | Gated entrance with security cabin | Gate, cabin, boom barrier | nos | - | - | Y | No | 2000000 | 2200000 | 2500000 | Yes
27 | F27 | Boundary & Entry | Street name / direction boards | Reflective sign boards | nos | Y | Y | Y | No | 3500 | 3850 | 4375 | Yes
28 | F28 | OSR / Park | OSR fencing | Chain-link around OSR | running m | Y | Y | Y | Yes | 1200 | 1320 | 1500 | Yes
29 | F29 | OSR / Park | Park landscaping | Lawn, shrubs, soil prep | sq m | - | Y | Y | No | 350 | 385 | 438 | Yes
30 | F30 | OSR / Park | Walking track | 1.5 m paver track | running m | - | Y | Y | No | 2500 | 2750 | 3125 | Yes
31 | F31 | OSR / Park | Children's play equipment | Swing, slide, see-saw set | sets | - | Y | Y | No | 250000 | 275000 | 312500 | Yes
32 | F32 | OSR / Park | Park benches | Granite / cast-iron | nos | - | Y | Y | No | 12000 | 13200 | 15000 | Yes
33 | F33 | OSR / Park | Outdoor gym | 6–8 station set | sets | - | - | Y | No | 400000 | 440000 | 500000 | Yes
34 | F34 | OSR / Park | Avenue trees | Sapling with tree guard | nos | Y | Y | Y | No | 1500 | 1650 | 1875 | Yes
35 | F35 | Premium Amenities | Clubhouse | RCC building incl. finishes | sq ft | - | - | Y | No | 2800 | 3080 | 3500 | Yes
36 | F36 | Premium Amenities | Swimming pool | RCC pool with filtration | sq m | - | - | Y | No | 30000 | 33000 | 37500 | Yes
37 | F37 | Premium Amenities | CCTV surveillance | IP camera incl. cabling & NVR share | nos | - | - | Y | No | 18000 | 19800 | 22500 | Yes
38 | F38 | Premium Amenities | Telecom / fibre duct | HDPE duct along roads | running m | - | - | Y | No | 450 | 495 | 562 | Yes
39 | F39 | Premium Amenities | EV charging point | 7 kW AC charger | nos | - | - | Y | No | 150000 | 165000 | 187500 | Yes
40 | F40 | Common | Solid waste collection point | Bin platform with shed | nos | Y | Y | Y | No | 50000 | 55000 | 62500 | Yes
Town / City costs pre-filled at 1.10× / 1.25× the Village rate – overwrite with the tenant's own rates.

## Document Checklist
Document Checklist – Master
One row per document, mapped to a Stage and to the exact Task ID for each area (N/A = not applicable).
Sino | Checklist | Doc ID | Applies To | Document / Item | Issued By / Source | Submission Format | Mandatory | Condition / Remarks | Stage No | Stage | Village Task ID | Town Task ID | City Task ID | Active
1 | Agri NOC | AGR-01 | All | Land-use conversion application form | Owner / Consultant | Online upload | Yes | Under TN CLU Rules 2017 (as amended) or zone reclassification | 3 | Change of Land Use / Zone Conversion | V3.1 | T3.1 | C3.1 | Yes
2 | Agri NOC | AGR-02 | All | Patta and Chitta | Revenue (e-Services) | Online copy | Yes |  | 1 | Land Due Diligence | V1.1 | T1.1 | C1.1 | Yes
3 | Agri NOC | AGR-03 | All | A-register / Adangal extract | Revenue (e-Services) | Online copy | Yes | Shows dry (punjai) / wet (nanjai) classification | 2 | Classification & Feasibility | V2.1 | T2.1 | C2.1 | Yes
4 | Agri NOC | AGR-04 | All | FMB sketch | Survey dept | Online copy | Yes |  | 1 | Land Due Diligence | V1.1 | T1.1 | C1.1 | Yes
5 | Agri NOC | AGR-05 | All | Encumbrance Certificate (30+ years) | Sub-Registrar / TNREGINET | Online copy | Yes |  | 1 | Land Due Diligence | V1.2 | T1.2 | C1.2 | Yes
6 | Agri NOC | AGR-06 | All | Sale deed / parent title documents | Owner | Self-attested copy | Yes |  | 1 | Land Due Diligence | V1.3 | T1.3 | C1.3 | Yes
7 | Agri NOC | AGR-07 | All | Site location sketch with surroundings | Licensed Surveyor | Drawing (PDF) | Yes | Show roads, water bodies, adjoining uses within 500 m | 4 | Layout Design | V4.3 | T4.3 | C4.3 | Yes
8 | Agri NOC | AGR-08 | All | Site photographs (all sides) | Owner | Images | Yes | Geo-tagged preferred | 2 | Classification & Feasibility | V2.1 | T2.1 | C2.1 | Yes
9 | Agri NOC | AGR-09 | All | Land classification certificate | VAO / Tahsildar | Original | Conditional | If classification is disputed or not clear in A-register | 2 | Classification & Feasibility | V2.1 | T2.1 | C2.1 | Yes
10 | Agri NOC | AGR-10 | All | Agriculture Department NOC | Joint Director of Agriculture | Original | Conditional | Wet land or where required; dry land in non-planning areas no longer needs Agri report after G.O. 149 (2026) | 3 | Change of Land Use / Zone Conversion | V3.3 | T3.3 | C3.3 | Yes
11 | Agri NOC | AGR-11 | All | WRD / PWD NOC | Water Resources Dept | Original | Conditional | If near tank, channel, river or in catchment | 5 | NOCs | V5.2 | T5.2 | C5.2 | Yes
12 | Agri NOC | AGR-12 | All | Affidavit – no tenancy / not irrigated / no dispute | Owner (notarised) | Original | Yes |  | 3 | Change of Land Use / Zone Conversion | V3.1 | T3.1 | C3.1 | Yes
13 | Agri NOC | AGR-13 | All | Owner ID and address proof (Aadhaar, PAN) | Owner | Self-attested copy | Yes |  | 3 | Change of Land Use / Zone Conversion | V3.1 | T3.1 | C3.1 | Yes
14 | Agri NOC | AGR-14 | All | Power of Attorney | Owner / SRO | Registered copy | Conditional | If applicant is not the owner | 3 | Change of Land Use / Zone Conversion | V3.1 | T3.1 | C3.1 | Yes
15 | Agri NOC | AGR-15 | All | Conversion fee challan | Owner | Receipt | Yes |  | 3 | Change of Land Use / Zone Conversion | V3.4 | T3.5 | C3.5 | Yes
16 | Agri NOC | AGR-16 | All | CLU / Reclassification order | DTCP / Govt (H&UD) | Original | Yes | Final output of this checklist | 3 | Change of Land Use / Zone Conversion | V3.5 | T3.6 | C3.6 | Yes
17 | DTCP Approval | DTC-01 | All | Layout application form (online portal) | Owner / Consultant | Online upload | Yes |  | 6 | Layout Application | V6.2 | T6.2 | C6.2 | Yes
18 | DTCP Approval | DTC-02 | All | Ownership set – sale deed, patta, chitta, A-register, FMB | Owner | Self-attested copy | Yes |  | 6 | Layout Application | V6.2 | T6.2 | C6.2 | Yes
19 | DTCP Approval | DTC-03 | All | Encumbrance Certificate (latest) | TNREGINET | Online copy | Yes |  | 6 | Layout Application | V6.2 | T6.2 | C6.2 | Yes
20 | DTCP Approval | DTC-04 | All | Legal title opinion | Panel advocate | Original | Yes | Advocate on local body / nationalised bank panel | 1 | Land Due Diligence | V1.3 | T1.3 | C1.3 | Yes
21 | DTCP Approval | DTC-05 | All | CLU order / zone certificate | DTCP / LPA | Copy | Yes |  | 6 | Layout Application | V6.2 | T6.2 | C6.2 | Yes
22 | DTCP Approval | DTC-06 | All | Topographic survey drawing | Licensed Surveyor | Drawing (PDF + CAD) | Yes |  | 4 | Layout Design | V4.2 | T4.2 | C4.2 | Yes
23 | DTCP Approval | DTC-07 | All | Layout plan – roads, OSR, public purpose, plot schedule | Registered Architect / Planner | Drawing (PDF + CAD) | Yes | As per TNCDBR 2019 | 4 | Layout Design | V4.3 | T4.3 | C4.3 | Yes
24 | DTCP Approval | DTC-08 | All | Key plan / location plan | Architect | Drawing (PDF) | Yes |  | 4 | Layout Design | V4.3 | T4.3 | C4.3 | Yes
25 | DTCP Approval | DTC-09 | All | Access-road certificate (Annexure-XVII) | BDO / EO / Commissioner | Original | Yes | Based on local body road register | 5 | NOCs | V5.5 | T5.5 | C5.5 | Yes
26 | DTCP Approval | DTC-10 | All | Undertaking in Form-C (Annexure-III, TNCDBR 2019) | Owner (notarised) | Original | Yes |  | 6 | Layout Application | V6.2 | T6.2 | C6.2 | Yes
27 | DTCP Approval | DTC-11 | All | Applicable NOCs (WRD, Highways, others) | Respective depts | Original | Conditional | As identified in NOC checklist | 5 | NOCs | V5.1 | T5.1 | C5.1 | Yes
28 | DTCP Approval | DTC-12 | All | Surveyor / Architect registration certificates | Consultants | Copy | Yes |  | 6 | Layout Application | V6.2 | T6.2 | C6.2 | Yes
29 | DTCP Approval | DTC-13 | All | Scrutiny fee receipt | Portal | Receipt | Yes |  | 6 | Layout Application | V6.3 | T6.3 | C6.3 | Yes
30 | DTCP Approval | DTC-14 | All | Compliance reply / revised drawings | Architect | Drawing (PDF) | Conditional | If objections raised at scrutiny | 7 | Scrutiny | V7.2 | T7.2 | C7.2 | Yes
31 | DTCP Approval | DTC-15 | All | Payment receipts – development, infrastructure & amenities, OSR charges | Owner | Receipt | Yes | As per demand notice | 8 | Charges | V8.2 | T8.2 | C8.2 | Yes
32 | DTCP Approval | DTC-16 | All | Registered gift deed copy (roads & OSR) | SRO | Certified copy | Yes | See Gift Deed checklist | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
33 | DTCP Approval | DTC-17 | All | Approval proceedings with LP number | DTCP | Original | Yes | Verify on onlineppa.tn.gov.in | 9 | Handover (Gift Deed) | V9.2 | T9.2 | C9.2 | Yes
34 | Local BDO Approval | BDO-01 | Village | Application routed through Panchayat Union | Owner | Online upload / Hard copy | Yes | DTCP accepts layouts only via the local body | 6 | Layout Application | V6.2 | N/A | N/A | Yes
35 | Local BDO Approval | BDO-02 | Village | Village Panchayat resolution / no-objection | Village Panchayat | Original | Yes |  | 5 | NOCs | V5.4 | N/A | N/A | Yes
36 | Local BDO Approval | BDO-03 | Village | Access-road certificate (Annexure-XVII) from road register | BDO, Panchayat Union | Original | Yes |  | 5 | NOCs | V5.5 | N/A | N/A | Yes
37 | Local BDO Approval | BDO-04 | Village | BDO scrutiny and forwarding letter to DTCP | BDO, Panchayat Union | Letter | Yes |  | 6 | Layout Application | V6.4 | N/A | N/A | Yes
38 | Local BDO Approval | BDO-05 | Village | DTCP technical sanction copy | DTCP | Copy | Yes |  | 9 | Handover (Gift Deed) | V9.2 | N/A | N/A | Yes
39 | Local BDO Approval | BDO-06 | Village | Panchayat development charges receipt | Panchayat Union | Receipt | Yes |  | 8 | Charges | V8.2 | N/A | N/A | Yes
40 | Local BDO Approval | BDO-07 | Village | Registered gift deed in favour of Village Panchayat | SRO | Certified copy | Yes | Accepted by BDO | 9 | Handover (Gift Deed) | V9.1 | N/A | N/A | Yes
41 | Local BDO Approval | BDO-08 | Village | Undertaking to form roads, drains, streetlights | Owner (notarised) | Original | Yes |  | 9 | Handover (Gift Deed) | V9.1 | N/A | N/A | Yes
42 | Local BDO Approval | BDO-09 | Village | BDO final layout approval order | BDO, Panchayat Union | Original | Yes | Executive Authority approval – TN Panchayat Building Rules | 9 | Handover (Gift Deed) | V9.3 | N/A | N/A | Yes
43 | Local BDO Approval | BDO-10 | Village | Completion inspection report of development works | Panchayat Union | Report | Yes |  | 10 | Development Works | V10.6 | N/A | N/A | Yes
44 | Local BDO Approval | BDO-11 | Village | Plot release letter for registration | BDO, Panchayat Union | Original | Yes |  | 11 | Final Approval & Release | V11.1 | N/A | N/A | Yes
45 | Town Approval | TWN-01 | Town | Master Plan zone certificate / extract | Local Planning Authority | Original | Yes |  | 2 | Classification & Feasibility | N/A | T2.2 | N/A | Yes
46 | Town Approval | TWN-02 | Town | Zone reclassification order | Govt (H&UD) / DTCP | Copy | Conditional | If land is not already in residential zone | 3 | Change of Land Use / Zone Conversion | N/A | T3.6 | N/A | Yes
47 | Town Approval | TWN-03 | Town | Application to Executive Officer / Municipal Commissioner | Owner | Online upload | Yes |  | 6 | Layout Application | N/A | T6.2 | N/A | Yes
48 | Town Approval | TWN-04 | Town | Access-road certificate (Annexure-XVII) | EO / Municipal Commissioner | Original | Yes |  | 5 | NOCs | N/A | T5.5 | N/A | Yes
49 | Town Approval | TWN-05 | Town | Water supply and drainage feasibility letter | Town Panchayat / Municipality | Original | Yes |  | 5 | NOCs | N/A | T5.6 | N/A | Yes
50 | Town Approval | TWN-06 | Town | Vacant land tax / property tax receipt | Town Panchayat / Municipality | Receipt | Yes |  | 6 | Layout Application | N/A | T6.2 | N/A | Yes
51 | Town Approval | TWN-07 | Town | Local body no-objection | Town Panchayat / Municipality | Original | Yes |  | 5 | NOCs | N/A | T5.4 | N/A | Yes
52 | Town Approval | TWN-08 | Town | Development / infrastructure charges receipt | Town Panchayat / Municipality | Receipt | Yes |  | 8 | Charges | N/A | T8.2 | N/A | Yes
53 | Town Approval | TWN-09 | Town | Registered gift deed in favour of Town Panchayat / Municipality | SRO | Certified copy | Yes |  | 9 | Handover (Gift Deed) | N/A | T9.1 | N/A | Yes
54 | Town Approval | TWN-10 | Town | Completion inspection report | Town Panchayat / Municipality | Report | Yes |  | 10 | Development Works | N/A | T10.6 | N/A | Yes
55 | Town Approval | TWN-11 | Town | Plot release letter | Town Panchayat / Municipality | Original | Yes |  | 11 | Final Approval & Release | N/A | T11.1 | N/A | Yes
56 | City Approval | CTY-01 | City | Master Plan / DDP zone certificate | DTCP / LPA / CMDA | Original | Yes | CMDA inside Chennai Metropolitan Area | 2 | Classification & Feasibility | N/A | N/A | C2.2 | Yes
57 | City Approval | CTY-02 | City | Government reclassification order (G.O.) | Govt (H&UD) | Copy | Conditional | If not residential zone | 3 | Change of Land Use / Zone Conversion | N/A | N/A | C3.6 | Yes
58 | City Approval | CTY-03 | City | Application to Corporation (online) | Owner | Online upload | Yes |  | 6 | Layout Application | N/A | N/A | C6.2 | Yes
59 | City Approval | CTY-04 | City | Access-road certificate (Annexure-XVII) | Corporation Commissioner | Original | Yes |  | 5 | NOCs | N/A | N/A | C5.5 | Yes
60 | City Approval | CTY-05 | City | Vacant land tax receipt | City Corporation | Receipt | Yes |  | 6 | Layout Application | N/A | N/A | C6.2 | Yes
61 | City Approval | CTY-06 | City | Water supply and sewerage feasibility | Corporation / Metro Water | Original | Yes |  | 5 | NOCs | N/A | N/A | C5.6 | Yes
62 | City Approval | CTY-07 | City | Highways / traffic NOC | NHAI / State Highways / Traffic Police | Original | Conditional | If abutting NH/SH or major road | 5 | NOCs | N/A | N/A | C5.3 | Yes
63 | City Approval | CTY-08 | City | Airport (AAI) NOC | Airports Authority of India | Original | Conditional | If within airport height-restriction zone | 5 | NOCs | N/A | N/A | C5.7 | Yes
64 | City Approval | CTY-09 | City | Railway NOC | Southern Railway | Original | Conditional | If near railway boundary | 5 | NOCs | N/A | N/A | C5.7 | Yes
65 | City Approval | CTY-10 | City | Fire & Rescue NOC | TN Fire & Rescue Services | Original | Conditional | If clubhouse / special building proposed | 5 | NOCs | N/A | N/A | C5.7 | Yes
66 | City Approval | CTY-11 | City | Development, infrastructure & OSR charges receipts | City Corporation / DTCP | Receipt | Yes |  | 8 | Charges | N/A | N/A | C8.2 | Yes
67 | City Approval | CTY-12 | City | Registered gift deed in favour of Corporation | SRO | Certified copy | Yes |  | 9 | Handover (Gift Deed) | N/A | N/A | C9.1 | Yes
68 | City Approval | CTY-13 | City | Completion inspection report | City Corporation | Report | Yes |  | 10 | Development Works | N/A | N/A | C10.6 | Yes
69 | City Approval | CTY-14 | City | Plot release letter | City Corporation | Original | Yes |  | 11 | Final Approval & Release | N/A | N/A | C11.1 | Yes
70 | Gift Deed | GFT-01 | All | Draft gift deed (roads, OSR, public-purpose areas) | Advocate | Draft | Yes | Donee: Village Panchayat / Town Panchayat / Municipality / Corporation | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
71 | Gift Deed | GFT-02 | All | Approved layout plan copy with road / OSR dimensions | DTCP | Copy | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
72 | Gift Deed | GFT-03 | All | Schedule of property – survey nos., extents, boundaries | Licensed Surveyor | Annexure | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
73 | Gift Deed | GFT-04 | All | Title documents, patta and latest EC | Owner | Self-attested copy | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
74 | Gift Deed | GFT-05 | All | Donor ID proof and photographs | Owner | Self-attested copy | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
75 | Gift Deed | GFT-06 | All | Local body acceptance / resolution | Local body / BDO | Original | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
76 | Gift Deed | GFT-07 | All | Two witnesses with ID proof | Owner | Copy | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
77 | Gift Deed | GFT-08 | All | Stamp duty and registration fee payment | SRO | Receipt | Yes | As applicable for gift to local body | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
78 | Gift Deed | GFT-09 | All | Registered gift deed | SRO | Original + certified copy | Yes | Submit copy to DTCP and local body | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
79 | Gift Deed | GFT-10 | All | Mutation of roads / OSR in local body records | Local body / Revenue | Letter | Yes |  | 9 | Handover (Gift Deed) | V9.1 | T9.1 | C9.1 | Yes
80 | RERA | RER-01 | All | Applicability check (>500 sq m or >8 plots) | Consultant | Note | Yes |  | 12 | RERA | V12.1 | T12.1 | C12.1 | Yes
81 | RERA | RER-02 | All | Promoter PAN, Aadhaar, photograph | Promoter | Self-attested copy | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
82 | RERA | RER-03 | All | Entity documents – incorporation / partnership deed / board resolution | Promoter | Copy | Conditional | If promoter is a company, firm or LLP | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
83 | RERA | RER-04 | All | Approved layout proceedings and plan (LP number) | DTCP / local body | Copy | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
84 | RERA | RER-05 | All | Title documents and legal title report | Advocate | Copy | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
85 | RERA | RER-06 | All | Latest Encumbrance Certificate | TNREGINET | Online copy | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
86 | RERA | RER-07 | All | Joint development / collaboration agreement | Owner & Promoter | Registered copy | Conditional | If land is not owned by promoter | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
87 | RERA | RER-08 | All | Separate project bank account letter (70% rule) | Bank | Original | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
88 | RERA | RER-09 | All | Project schedule and development works details | Promoter / Engineer | Document | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
89 | RERA | RER-10 | All | Proforma allotment letter and agreement for sale | Advocate | Draft | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
90 | RERA | RER-11 | All | Declaration / affidavit (Form B) | Promoter (notarised) | Original | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
91 | RERA | RER-12 | All | Details of promoter's past projects (5 years) | Promoter | Document | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
92 | RERA | RER-13 | All | Brochure / advertisement draft with RERA number placeholder | Promoter | Document | Yes | No advertising before registration | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
93 | RERA | RER-14 | All | Registration fee receipt | TNRERA portal | Receipt | Yes |  | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
94 | RERA | RER-15 | All | TNRERA registration certificate | TNRERA | Original | Yes | Display number on all ads and site boards | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
95 | Plot Sale | SAL-01 | All | Approved layout copy with LP number | DTCP / local body | Copy | Yes | Share with buyer | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
96 | Plot Sale | SAL-02 | All | Plot release letter | BDO / local body | Copy | Yes |  | 11 | Final Approval & Release | V11.1 | T11.1 | C11.1 | Yes
97 | Plot Sale | SAL-03 | All | RERA registration number | TNRERA | Copy | Conditional | If project is RERA-registrable | 12 | RERA | V12.2 | T12.2 | C12.2 | Yes
98 | Plot Sale | SAL-04 | All | Parent title documents and latest EC | Promoter | Copy | Yes |  | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
99 | Plot Sale | SAL-05 | All | Plot sub-division / individual patta | Taluk office | Copy | Yes |  | 13 | Sub-division & Sale | V13.1 | T13.1 | C13.1 | Yes
100 | Plot Sale | SAL-06 | All | Buyer KYC – PAN, Aadhaar, photographs | Buyer | Self-attested copy | Yes |  | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
101 | Plot Sale | SAL-07 | All | Booking form and booking amount receipt | Promoter | Original | Yes | Valid for Booking Validity days (Additional Settings) | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
102 | Plot Sale | SAL-08 | All | Allotment letter | Promoter | Original | Yes |  | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
103 | Plot Sale | SAL-09 | All | Agreement for sale | Promoter & Buyer | Registered / Signed | Yes | Instalment schedule per Additional Settings | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
104 | Plot Sale | SAL-10 | All | Instalment payment receipts | Promoter | Receipt | Yes |  | 13 | Sub-division & Sale | V13.2 | T13.2 | C13.2 | Yes
105 | Plot Sale | SAL-11 | All | Bank NOC / loan sanction letter | Bank | Original | Conditional | If land mortgaged or buyer takes a loan | 13 | Sub-division & Sale | V13.3 | T13.3 | C13.3 | Yes
106 | Plot Sale | SAL-12 | All | TDS (1%) challan – Form 26QB | Buyer | Receipt | Conditional | If sale value ≥ ₹50 lakh (Sec. 194-IA) | 13 | Sub-division & Sale | V13.3 | T13.3 | C13.3 | Yes
107 | Plot Sale | SAL-13 | All | Stamp duty and registration fee payment | Buyer / SRO | Receipt | Yes | On guideline value or sale value, whichever is higher | 13 | Sub-division & Sale | V13.3 | T13.3 | C13.3 | Yes
108 | Plot Sale | SAL-14 | All | Registered sale deed | SRO | Original | Yes | Within Sale Completion Window (Additional Settings) | 13 | Sub-division & Sale | V13.3 | T13.3 | C13.3 | Yes
109 | Plot Sale | SAL-15 | All | Possession / handover letter | Promoter | Original | Yes |  | 13 | Sub-division & Sale | V13.3 | T13.3 | C13.3 | Yes
110 | Plot Sale | SAL-16 | All | Patta transfer application / order | Taluk office | Receipt / Order | Yes |  | 13 | Sub-division & Sale | V13.4 | T13.4 | C13.4 | Yes

## Stage Checklist Map
Stage × Checklist Map
Top: number of documents per Stage and Checklist (live from Document Checklist). Bottom: flat Task → Document mapping for import.
Stage No | Stage | Agri NOC | DTCP Approval | Local BDO Approval | Town Approval | City Approval | Gift Deed | RERA | Plot Sale | Total
1 | Land Due Diligence | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 5
2 | Classification & Feasibility | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 5
3 | Change of Land Use / Zone Conversion | 7 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 9
4 | Layout Design | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4
5 | NOCs | 1 | 2 | 2 | 3 | 6 | 0 | 0 | 0 | 14
6 | Layout Application | 0 | 7 | 2 | 2 | 2 | 0 | 0 | 0 | 13
7 | Scrutiny | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
8 | Charges | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 4
9 | Handover (Gift Deed) | 0 | 2 | 4 | 1 | 1 | 10 | 0 | 0 | 18
10 | Development Works | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 3
11 | Final Approval & Release | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 4
12 | RERA | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 1 | 16
13 | Sub-division & Sale | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14
| Total | 16 | 17 | 11 | 11 | 14 | 10 | 15 | 16 | 110
Task → Document mapping (one row per area, task and document)
Sino | Area Type | Stage No | Stage | Task ID | Short Name | Checklist | Doc ID | Document / Item | Mandatory
1 | Village | 1 | Land Due Diligence | V1.1 | Land Records | Agri NOC | AGR-02 | Patta and Chitta | Yes
2 | Village | 1 | Land Due Diligence | V1.1 | Land Records | Agri NOC | AGR-04 | FMB sketch | Yes
3 | Village | 1 | Land Due Diligence | V1.2 | EC 30 Yrs | Agri NOC | AGR-05 | Encumbrance Certificate (30+ years) | Yes
4 | Village | 1 | Land Due Diligence | V1.3 | Title Opinion | Agri NOC | AGR-06 | Sale deed / parent title documents | Yes
5 | Village | 1 | Land Due Diligence | V1.3 | Title Opinion | DTCP Approval | DTC-04 | Legal title opinion | Yes
6 | Village | 2 | Classification & Feasibility | V2.1 | Dry/Wet Check | Agri NOC | AGR-03 | A-register / Adangal extract | Yes
7 | Village | 2 | Classification & Feasibility | V2.1 | Dry/Wet Check | Agri NOC | AGR-08 | Site photographs (all sides) | Yes
8 | Village | 2 | Classification & Feasibility | V2.1 | Dry/Wet Check | Agri NOC | AGR-09 | Land classification certificate | Conditional
9 | Village | 3 | Change of Land Use (CLU) | V3.1 | CLU Application | Agri NOC | AGR-01 | Land-use conversion application form | Yes
10 | Village | 3 | Change of Land Use (CLU) | V3.1 | CLU Application | Agri NOC | AGR-12 | Affidavit – no tenancy / not irrigated / no dispute | Yes
11 | Village | 3 | Change of Land Use (CLU) | V3.1 | CLU Application | Agri NOC | AGR-13 | Owner ID and address proof (Aadhaar, PAN) | Yes
12 | Village | 3 | Change of Land Use (CLU) | V3.1 | CLU Application | Agri NOC | AGR-14 | Power of Attorney | Conditional
13 | Village | 3 | Change of Land Use (CLU) | V3.3 | CLU Inspection | Agri NOC | AGR-10 | Agriculture Department NOC | Conditional
14 | Village | 3 | Change of Land Use (CLU) | V3.4 | CLU Fees | Agri NOC | AGR-15 | Conversion fee challan | Yes
15 | Village | 3 | Change of Land Use (CLU) | V3.5 | CLU Order | Agri NOC | AGR-16 | CLU / Reclassification order | Yes
16 | Village | 4 | Layout Design | V4.2 | Topo Survey | DTCP Approval | DTC-06 | Topographic survey drawing | Yes
17 | Village | 4 | Layout Design | V4.3 | Draft Layout | Agri NOC | AGR-07 | Site location sketch with surroundings | Yes
18 | Village | 4 | Layout Design | V4.3 | Draft Layout | DTCP Approval | DTC-07 | Layout plan – roads, OSR, public purpose, plot schedule | Yes
19 | Village | 4 | Layout Design | V4.3 | Draft Layout | DTCP Approval | DTC-08 | Key plan / location plan | Yes
20 | Village | 5 | NOCs | V5.1 | NOC Checklist | DTCP Approval | DTC-11 | Applicable NOCs (WRD, Highways, others) | Conditional
21 | Village | 5 | NOCs | V5.2 | WRD NOC | Agri NOC | AGR-11 | WRD / PWD NOC | Conditional
22 | Village | 5 | NOCs | V5.4 | Local Body NOC | Local BDO Approval | BDO-02 | Village Panchayat resolution / no-objection | Yes
23 | Village | 5 | NOCs | V5.5 | Access Road Cert | Local BDO Approval | BDO-03 | Access-road certificate (Annexure-XVII) from road register | Yes
24 | Village | 5 | NOCs | V5.5 | Access Road Cert | DTCP Approval | DTC-09 | Access-road certificate (Annexure-XVII) | Yes
25 | Village | 6 | Layout Application | V6.2 | Submit Application | Local BDO Approval | BDO-01 | Application routed through Panchayat Union | Yes
26 | Village | 6 | Layout Application | V6.2 | Submit Application | DTCP Approval | DTC-01 | Layout application form (online portal) | Yes
27 | Village | 6 | Layout Application | V6.2 | Submit Application | DTCP Approval | DTC-02 | Ownership set – sale deed, patta, chitta, A-register, FMB | Yes
28 | Village | 6 | Layout Application | V6.2 | Submit Application | DTCP Approval | DTC-03 | Encumbrance Certificate (latest) | Yes
29 | Village | 6 | Layout Application | V6.2 | Submit Application | DTCP Approval | DTC-05 | CLU order / zone certificate | Yes
30 | Village | 6 | Layout Application | V6.2 | Submit Application | DTCP Approval | DTC-10 | Undertaking in Form-C (Annexure-III, TNCDBR 2019) | Yes
31 | Village | 6 | Layout Application | V6.2 | Submit Application | DTCP Approval | DTC-12 | Surveyor / Architect registration certificates | Yes
32 | Village | 6 | Layout Application | V6.3 | Scrutiny Fees | DTCP Approval | DTC-13 | Scrutiny fee receipt | Yes
33 | Village | 6 | Layout Application | V6.4 | BDO Forwarding | Local BDO Approval | BDO-04 | BDO scrutiny and forwarding letter to DTCP | Yes
34 | Village | 7 | Scrutiny | V7.2 | Revise Drawings | DTCP Approval | DTC-14 | Compliance reply / revised drawings | Conditional
35 | Village | 8 | Charges | V8.2 | Pay Charges | Local BDO Approval | BDO-06 | Panchayat development charges receipt | Yes
36 | Village | 8 | Charges | V8.2 | Pay Charges | DTCP Approval | DTC-15 | Payment receipts – development, infrastructure & amenities, OSR charges | Yes
37 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Local BDO Approval | BDO-07 | Registered gift deed in favour of Village Panchayat | Yes
38 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Local BDO Approval | BDO-08 | Undertaking to form roads, drains, streetlights | Yes
39 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | DTCP Approval | DTC-16 | Registered gift deed copy (roads & OSR) | Yes
40 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-01 | Draft gift deed (roads, OSR, public-purpose areas) | Yes
41 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-02 | Approved layout plan copy with road / OSR dimensions | Yes
42 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-03 | Schedule of property – survey nos., extents, boundaries | Yes
43 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-04 | Title documents, patta and latest EC | Yes
44 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-05 | Donor ID proof and photographs | Yes
45 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-06 | Local body acceptance / resolution | Yes
46 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-07 | Two witnesses with ID proof | Yes
47 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-08 | Stamp duty and registration fee payment | Yes
48 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-09 | Registered gift deed | Yes
49 | Village | 9 | Handover (Gift Deed) | V9.1 | Gift Deed | Gift Deed | GFT-10 | Mutation of roads / OSR in local body records | Yes
50 | Village | 9 | Handover (Gift Deed) | V9.2 | DTCP Sanction | Local BDO Approval | BDO-05 | DTCP technical sanction copy | Yes
51 | Village | 9 | Handover (Gift Deed) | V9.2 | DTCP Sanction | DTCP Approval | DTC-17 | Approval proceedings with LP number | Yes
52 | Village | 9 | Handover (Gift Deed) | V9.3 | BDO Final Approval | Local BDO Approval | BDO-09 | BDO final layout approval order | Yes
53 | Village | 10 | Development Works | V10.6 | Completion Check | Local BDO Approval | BDO-10 | Completion inspection report of development works | Yes
54 | Village | 11 | Final Approval & Release | V11.1 | Plot Release | Local BDO Approval | BDO-11 | Plot release letter for registration | Yes
55 | Village | 11 | Final Approval & Release | V11.1 | Plot Release | Plot Sale | SAL-02 | Plot release letter | Yes
56 | Village | 12 | RERA | V12.1 | RERA Check | RERA | RER-01 | Applicability check (>500 sq m or >8 plots) | Yes
57 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-02 | Promoter PAN, Aadhaar, photograph | Yes
58 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-03 | Entity documents – incorporation / partnership deed / board resolution | Conditional
59 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-04 | Approved layout proceedings and plan (LP number) | Yes
60 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-05 | Title documents and legal title report | Yes
61 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-06 | Latest Encumbrance Certificate | Yes
62 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-07 | Joint development / collaboration agreement | Conditional
63 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-08 | Separate project bank account letter (70% rule) | Yes
64 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-09 | Project schedule and development works details | Yes
65 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-10 | Proforma allotment letter and agreement for sale | Yes
66 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-11 | Declaration / affidavit (Form B) | Yes
67 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-12 | Details of promoter's past projects (5 years) | Yes
68 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-13 | Brochure / advertisement draft with RERA number placeholder | Yes
69 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-14 | Registration fee receipt | Yes
70 | Village | 12 | RERA | V12.2 | RERA Registration | RERA | RER-15 | TNRERA registration certificate | Yes
71 | Village | 12 | RERA | V12.2 | RERA Registration | Plot Sale | SAL-03 | RERA registration number | Conditional
72 | Village | 13 | Sub-division & Sale | V13.1 | Sub-division | Plot Sale | SAL-05 | Plot sub-division / individual patta | Yes
73 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-01 | Approved layout copy with LP number | Yes
74 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-04 | Parent title documents and latest EC | Yes
75 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-06 | Buyer KYC – PAN, Aadhaar, photographs | Yes
76 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-07 | Booking form and booking amount receipt | Yes
77 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-08 | Allotment letter | Yes
78 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-09 | Agreement for sale | Yes
79 | Village | 13 | Sub-division & Sale | V13.2 | Marketing | Plot Sale | SAL-10 | Instalment payment receipts | Yes
80 | Village | 13 | Sub-division & Sale | V13.3 | Sale Deeds | Plot Sale | SAL-11 | Bank NOC / loan sanction letter | Conditional
81 | Village | 13 | Sub-division & Sale | V13.3 | Sale Deeds | Plot Sale | SAL-12 | TDS (1%) challan – Form 26QB | Conditional
82 | Village | 13 | Sub-division & Sale | V13.3 | Sale Deeds | Plot Sale | SAL-13 | Stamp duty and registration fee payment | Yes
83 | Village | 13 | Sub-division & Sale | V13.3 | Sale Deeds | Plot Sale | SAL-14 | Registered sale deed | Yes
84 | Village | 13 | Sub-division & Sale | V13.3 | Sale Deeds | Plot Sale | SAL-15 | Possession / handover letter | Yes
85 | Village | 13 | Sub-division & Sale | V13.4 | Patta Transfer | Plot Sale | SAL-16 | Patta transfer application / order | Yes
86 | Town | 1 | Land Due Diligence | T1.1 | Land Records | Agri NOC | AGR-02 | Patta and Chitta | Yes
87 | Town | 1 | Land Due Diligence | T1.1 | Land Records | Agri NOC | AGR-04 | FMB sketch | Yes
88 | Town | 1 | Land Due Diligence | T1.2 | EC 30 Yrs | Agri NOC | AGR-05 | Encumbrance Certificate (30+ years) | Yes
89 | Town | 1 | Land Due Diligence | T1.3 | Title Opinion | Agri NOC | AGR-06 | Sale deed / parent title documents | Yes
90 | Town | 1 | Land Due Diligence | T1.3 | Title Opinion | DTCP Approval | DTC-04 | Legal title opinion | Yes
91 | Town | 2 | Classification & Feasibility | T2.1 | Dry/Wet Check | Agri NOC | AGR-03 | A-register / Adangal extract | Yes
92 | Town | 2 | Classification & Feasibility | T2.1 | Dry/Wet Check | Agri NOC | AGR-08 | Site photographs (all sides) | Yes
93 | Town | 2 | Classification & Feasibility | T2.1 | Dry/Wet Check | Agri NOC | AGR-09 | Land classification certificate | Conditional
94 | Town | 2 | Classification & Feasibility | T2.2 | Zone Check | Town Approval | TWN-01 | Master Plan zone certificate / extract | Yes
95 | Town | 3 | Zone Conversion / CLU | T3.1 | Zone Application | Agri NOC | AGR-01 | Land-use conversion application form | Yes
96 | Town | 3 | Zone Conversion / CLU | T3.1 | Zone Application | Agri NOC | AGR-12 | Affidavit – no tenancy / not irrigated / no dispute | Yes
97 | Town | 3 | Zone Conversion / CLU | T3.1 | Zone Application | Agri NOC | AGR-13 | Owner ID and address proof (Aadhaar, PAN) | Yes
98 | Town | 3 | Zone Conversion / CLU | T3.1 | Zone Application | Agri NOC | AGR-14 | Power of Attorney | Conditional
99 | Town | 3 | Zone Conversion / CLU | T3.3 | Public Notice | Agri NOC | AGR-10 | Agriculture Department NOC | Conditional
100 | Town | 3 | Zone Conversion / CLU | T3.5 | Zone Fees | Agri NOC | AGR-15 | Conversion fee challan | Yes
101 | Town | 3 | Zone Conversion / CLU | T3.6 | Zone Order | Agri NOC | AGR-16 | CLU / Reclassification order | Yes
102 | Town | 3 | Zone Conversion / CLU | T3.6 | Zone Order | Town Approval | TWN-02 | Zone reclassification order | Conditional
103 | Town | 4 | Layout Design | T4.2 | Topo Survey | DTCP Approval | DTC-06 | Topographic survey drawing | Yes
104 | Town | 4 | Layout Design | T4.3 | Draft Layout | Agri NOC | AGR-07 | Site location sketch with surroundings | Yes
105 | Town | 4 | Layout Design | T4.3 | Draft Layout | DTCP Approval | DTC-07 | Layout plan – roads, OSR, public purpose, plot schedule | Yes
106 | Town | 4 | Layout Design | T4.3 | Draft Layout | DTCP Approval | DTC-08 | Key plan / location plan | Yes
107 | Town | 5 | NOCs | T5.1 | NOC Checklist | DTCP Approval | DTC-11 | Applicable NOCs (WRD, Highways, others) | Conditional
108 | Town | 5 | NOCs | T5.2 | WRD NOC | Agri NOC | AGR-11 | WRD / PWD NOC | Conditional
109 | Town | 5 | NOCs | T5.4 | Local Body NOC | Town Approval | TWN-07 | Local body no-objection | Yes
110 | Town | 5 | NOCs | T5.5 | Access Road Cert | DTCP Approval | DTC-09 | Access-road certificate (Annexure-XVII) | Yes
111 | Town | 5 | NOCs | T5.5 | Access Road Cert | Town Approval | TWN-04 | Access-road certificate (Annexure-XVII) | Yes
112 | Town | 5 | NOCs | T5.6 | Water/Drain Feasibility | Town Approval | TWN-05 | Water supply and drainage feasibility letter | Yes
113 | Town | 6 | Layout Application | T6.2 | Submit Application | DTCP Approval | DTC-01 | Layout application form (online portal) | Yes
114 | Town | 6 | Layout Application | T6.2 | Submit Application | DTCP Approval | DTC-02 | Ownership set – sale deed, patta, chitta, A-register, FMB | Yes
115 | Town | 6 | Layout Application | T6.2 | Submit Application | DTCP Approval | DTC-03 | Encumbrance Certificate (latest) | Yes
116 | Town | 6 | Layout Application | T6.2 | Submit Application | DTCP Approval | DTC-05 | CLU order / zone certificate | Yes
117 | Town | 6 | Layout Application | T6.2 | Submit Application | DTCP Approval | DTC-10 | Undertaking in Form-C (Annexure-III, TNCDBR 2019) | Yes
118 | Town | 6 | Layout Application | T6.2 | Submit Application | DTCP Approval | DTC-12 | Surveyor / Architect registration certificates | Yes
119 | Town | 6 | Layout Application | T6.2 | Submit Application | Town Approval | TWN-03 | Application to Executive Officer / Municipal Commissioner | Yes
120 | Town | 6 | Layout Application | T6.2 | Submit Application | Town Approval | TWN-06 | Vacant land tax / property tax receipt | Yes
121 | Town | 6 | Layout Application | T6.3 | Scrutiny Fees | DTCP Approval | DTC-13 | Scrutiny fee receipt | Yes
122 | Town | 7 | Scrutiny | T7.2 | Revise Drawings | DTCP Approval | DTC-14 | Compliance reply / revised drawings | Conditional
123 | Town | 8 | Charges | T8.2 | Pay Charges | DTCP Approval | DTC-15 | Payment receipts – development, infrastructure & amenities, OSR charges | Yes
124 | Town | 8 | Charges | T8.2 | Pay Charges | Town Approval | TWN-08 | Development / infrastructure charges receipt | Yes
125 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | DTCP Approval | DTC-16 | Registered gift deed copy (roads & OSR) | Yes
126 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-01 | Draft gift deed (roads, OSR, public-purpose areas) | Yes
127 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-02 | Approved layout plan copy with road / OSR dimensions | Yes
128 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-03 | Schedule of property – survey nos., extents, boundaries | Yes
129 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-04 | Title documents, patta and latest EC | Yes
130 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-05 | Donor ID proof and photographs | Yes
131 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-06 | Local body acceptance / resolution | Yes
132 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-07 | Two witnesses with ID proof | Yes
133 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-08 | Stamp duty and registration fee payment | Yes
134 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-09 | Registered gift deed | Yes
135 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Gift Deed | GFT-10 | Mutation of roads / OSR in local body records | Yes
136 | Town | 9 | Handover (Gift Deed) | T9.1 | Gift Deed | Town Approval | TWN-09 | Registered gift deed in favour of Town Panchayat / Municipality | Yes
137 | Town | 9 | Handover (Gift Deed) | T9.2 | Layout Approval | DTCP Approval | DTC-17 | Approval proceedings with LP number | Yes
138 | Town | 10 | Development Works | T10.6 | Completion Check | Town Approval | TWN-10 | Completion inspection report | Yes
139 | Town | 11 | Final Approval & Release | T11.1 | Plot Release | Plot Sale | SAL-02 | Plot release letter | Yes
140 | Town | 11 | Final Approval & Release | T11.1 | Plot Release | Town Approval | TWN-11 | Plot release letter | Yes
141 | Town | 12 | RERA | T12.1 | RERA Check | RERA | RER-01 | Applicability check (>500 sq m or >8 plots) | Yes
142 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-02 | Promoter PAN, Aadhaar, photograph | Yes
143 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-03 | Entity documents – incorporation / partnership deed / board resolution | Conditional
144 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-04 | Approved layout proceedings and plan (LP number) | Yes
145 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-05 | Title documents and legal title report | Yes
146 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-06 | Latest Encumbrance Certificate | Yes
147 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-07 | Joint development / collaboration agreement | Conditional
148 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-08 | Separate project bank account letter (70% rule) | Yes
149 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-09 | Project schedule and development works details | Yes
150 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-10 | Proforma allotment letter and agreement for sale | Yes
151 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-11 | Declaration / affidavit (Form B) | Yes
152 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-12 | Details of promoter's past projects (5 years) | Yes
153 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-13 | Brochure / advertisement draft with RERA number placeholder | Yes
154 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-14 | Registration fee receipt | Yes
155 | Town | 12 | RERA | T12.2 | RERA Registration | RERA | RER-15 | TNRERA registration certificate | Yes
156 | Town | 12 | RERA | T12.2 | RERA Registration | Plot Sale | SAL-03 | RERA registration number | Conditional
157 | Town | 13 | Sub-division & Sale | T13.1 | Sub-division | Plot Sale | SAL-05 | Plot sub-division / individual patta | Yes
158 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-01 | Approved layout copy with LP number | Yes
159 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-04 | Parent title documents and latest EC | Yes
160 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-06 | Buyer KYC – PAN, Aadhaar, photographs | Yes
161 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-07 | Booking form and booking amount receipt | Yes
162 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-08 | Allotment letter | Yes
163 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-09 | Agreement for sale | Yes
164 | Town | 13 | Sub-division & Sale | T13.2 | Marketing | Plot Sale | SAL-10 | Instalment payment receipts | Yes
165 | Town | 13 | Sub-division & Sale | T13.3 | Sale Deeds | Plot Sale | SAL-11 | Bank NOC / loan sanction letter | Conditional
166 | Town | 13 | Sub-division & Sale | T13.3 | Sale Deeds | Plot Sale | SAL-12 | TDS (1%) challan – Form 26QB | Conditional
167 | Town | 13 | Sub-division & Sale | T13.3 | Sale Deeds | Plot Sale | SAL-13 | Stamp duty and registration fee payment | Yes
168 | Town | 13 | Sub-division & Sale | T13.3 | Sale Deeds | Plot Sale | SAL-14 | Registered sale deed | Yes
169 | Town | 13 | Sub-division & Sale | T13.3 | Sale Deeds | Plot Sale | SAL-15 | Possession / handover letter | Yes
170 | Town | 13 | Sub-division & Sale | T13.4 | Patta Transfer | Plot Sale | SAL-16 | Patta transfer application / order | Yes
171 | City | 1 | Land Due Diligence | C1.1 | Land Records | Agri NOC | AGR-02 | Patta and Chitta | Yes
172 | City | 1 | Land Due Diligence | C1.1 | Land Records | Agri NOC | AGR-04 | FMB sketch | Yes
173 | City | 1 | Land Due Diligence | C1.2 | EC 30 Yrs | Agri NOC | AGR-05 | Encumbrance Certificate (30+ years) | Yes
174 | City | 1 | Land Due Diligence | C1.3 | Title Opinion | Agri NOC | AGR-06 | Sale deed / parent title documents | Yes
175 | City | 1 | Land Due Diligence | C1.3 | Title Opinion | DTCP Approval | DTC-04 | Legal title opinion | Yes
176 | City | 2 | Classification & Feasibility | C2.1 | Dry/Wet Check | Agri NOC | AGR-03 | A-register / Adangal extract | Yes
177 | City | 2 | Classification & Feasibility | C2.1 | Dry/Wet Check | Agri NOC | AGR-08 | Site photographs (all sides) | Yes
178 | City | 2 | Classification & Feasibility | C2.1 | Dry/Wet Check | Agri NOC | AGR-09 | Land classification certificate | Conditional
179 | City | 2 | Classification & Feasibility | C2.2 | Zone Check | City Approval | CTY-01 | Master Plan / DDP zone certificate | Yes
180 | City | 3 | Zone Conversion / CLU | C3.1 | Zone Application | Agri NOC | AGR-01 | Land-use conversion application form | Yes
181 | City | 3 | Zone Conversion / CLU | C3.1 | Zone Application | Agri NOC | AGR-12 | Affidavit – no tenancy / not irrigated / no dispute | Yes
182 | City | 3 | Zone Conversion / CLU | C3.1 | Zone Application | Agri NOC | AGR-13 | Owner ID and address proof (Aadhaar, PAN) | Yes
183 | City | 3 | Zone Conversion / CLU | C3.1 | Zone Application | Agri NOC | AGR-14 | Power of Attorney | Conditional
184 | City | 3 | Zone Conversion / CLU | C3.3 | Public Notice | Agri NOC | AGR-10 | Agriculture Department NOC | Conditional
185 | City | 3 | Zone Conversion / CLU | C3.5 | Zone Fees | Agri NOC | AGR-15 | Conversion fee challan | Yes
186 | City | 3 | Zone Conversion / CLU | C3.6 | Zone Order | Agri NOC | AGR-16 | CLU / Reclassification order | Yes
187 | City | 3 | Zone Conversion / CLU | C3.6 | Zone Order | City Approval | CTY-02 | Government reclassification order (G.O.) | Conditional
188 | City | 4 | Layout Design | C4.2 | Topo Survey | DTCP Approval | DTC-06 | Topographic survey drawing | Yes
189 | City | 4 | Layout Design | C4.3 | Draft Layout | Agri NOC | AGR-07 | Site location sketch with surroundings | Yes
190 | City | 4 | Layout Design | C4.3 | Draft Layout | DTCP Approval | DTC-07 | Layout plan – roads, OSR, public purpose, plot schedule | Yes
191 | City | 4 | Layout Design | C4.3 | Draft Layout | DTCP Approval | DTC-08 | Key plan / location plan | Yes
192 | City | 5 | NOCs | C5.1 | NOC Checklist | DTCP Approval | DTC-11 | Applicable NOCs (WRD, Highways, others) | Conditional
193 | City | 5 | NOCs | C5.2 | WRD NOC | Agri NOC | AGR-11 | WRD / PWD NOC | Conditional
194 | City | 5 | NOCs | C5.3 | Highways NOC | City Approval | CTY-07 | Highways / traffic NOC | Conditional
195 | City | 5 | NOCs | C5.5 | Access Road Cert | City Approval | CTY-04 | Access-road certificate (Annexure-XVII) | Yes
196 | City | 5 | NOCs | C5.5 | Access Road Cert | DTCP Approval | DTC-09 | Access-road certificate (Annexure-XVII) | Yes
197 | City | 5 | NOCs | C5.6 | Water/Drain Feasibility | City Approval | CTY-06 | Water supply and sewerage feasibility | Yes
198 | City | 5 | NOCs | C5.7 | Other NOCs | City Approval | CTY-08 | Airport (AAI) NOC | Conditional
199 | City | 5 | NOCs | C5.7 | Other NOCs | City Approval | CTY-09 | Railway NOC | Conditional
200 | City | 5 | NOCs | C5.7 | Other NOCs | City Approval | CTY-10 | Fire & Rescue NOC | Conditional
201 | City | 6 | Layout Application | C6.2 | Submit Application | City Approval | CTY-03 | Application to Corporation (online) | Yes
202 | City | 6 | Layout Application | C6.2 | Submit Application | City Approval | CTY-05 | Vacant land tax receipt | Yes
203 | City | 6 | Layout Application | C6.2 | Submit Application | DTCP Approval | DTC-01 | Layout application form (online portal) | Yes
204 | City | 6 | Layout Application | C6.2 | Submit Application | DTCP Approval | DTC-02 | Ownership set – sale deed, patta, chitta, A-register, FMB | Yes
205 | City | 6 | Layout Application | C6.2 | Submit Application | DTCP Approval | DTC-03 | Encumbrance Certificate (latest) | Yes
206 | City | 6 | Layout Application | C6.2 | Submit Application | DTCP Approval | DTC-05 | CLU order / zone certificate | Yes
207 | City | 6 | Layout Application | C6.2 | Submit Application | DTCP Approval | DTC-10 | Undertaking in Form-C (Annexure-III, TNCDBR 2019) | Yes
208 | City | 6 | Layout Application | C6.2 | Submit Application | DTCP Approval | DTC-12 | Surveyor / Architect registration certificates | Yes
209 | City | 6 | Layout Application | C6.3 | Scrutiny Fees | DTCP Approval | DTC-13 | Scrutiny fee receipt | Yes
210 | City | 7 | Scrutiny | C7.2 | Revise Drawings | DTCP Approval | DTC-14 | Compliance reply / revised drawings | Conditional
211 | City | 8 | Charges | C8.2 | Pay Charges | City Approval | CTY-11 | Development, infrastructure & OSR charges receipts | Yes
212 | City | 8 | Charges | C8.2 | Pay Charges | DTCP Approval | DTC-15 | Payment receipts – development, infrastructure & amenities, OSR charges | Yes
213 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | City Approval | CTY-12 | Registered gift deed in favour of Corporation | Yes
214 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | DTCP Approval | DTC-16 | Registered gift deed copy (roads & OSR) | Yes
215 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-01 | Draft gift deed (roads, OSR, public-purpose areas) | Yes
216 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-02 | Approved layout plan copy with road / OSR dimensions | Yes
217 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-03 | Schedule of property – survey nos., extents, boundaries | Yes
218 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-04 | Title documents, patta and latest EC | Yes
219 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-05 | Donor ID proof and photographs | Yes
220 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-06 | Local body acceptance / resolution | Yes
221 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-07 | Two witnesses with ID proof | Yes
222 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-08 | Stamp duty and registration fee payment | Yes
223 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-09 | Registered gift deed | Yes
224 | City | 9 | Handover (Gift Deed) | C9.1 | Gift Deed | Gift Deed | GFT-10 | Mutation of roads / OSR in local body records | Yes
225 | City | 9 | Handover (Gift Deed) | C9.2 | Layout Approval | DTCP Approval | DTC-17 | Approval proceedings with LP number | Yes
226 | City | 10 | Development Works | C10.6 | Completion Check | City Approval | CTY-13 | Completion inspection report | Yes
227 | City | 11 | Final Approval & Release | C11.1 | Plot Release | City Approval | CTY-14 | Plot release letter | Yes
228 | City | 11 | Final Approval & Release | C11.1 | Plot Release | Plot Sale | SAL-02 | Plot release letter | Yes
229 | City | 12 | RERA | C12.1 | RERA Check | RERA | RER-01 | Applicability check (>500 sq m or >8 plots) | Yes
230 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-02 | Promoter PAN, Aadhaar, photograph | Yes
231 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-03 | Entity documents – incorporation / partnership deed / board resolution | Conditional
232 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-04 | Approved layout proceedings and plan (LP number) | Yes
233 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-05 | Title documents and legal title report | Yes
234 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-06 | Latest Encumbrance Certificate | Yes
235 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-07 | Joint development / collaboration agreement | Conditional
236 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-08 | Separate project bank account letter (70% rule) | Yes
237 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-09 | Project schedule and development works details | Yes
238 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-10 | Proforma allotment letter and agreement for sale | Yes
239 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-11 | Declaration / affidavit (Form B) | Yes
240 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-12 | Details of promoter's past projects (5 years) | Yes
241 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-13 | Brochure / advertisement draft with RERA number placeholder | Yes
242 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-14 | Registration fee receipt | Yes
243 | City | 12 | RERA | C12.2 | RERA Registration | RERA | RER-15 | TNRERA registration certificate | Yes
244 | City | 12 | RERA | C12.2 | RERA Registration | Plot Sale | SAL-03 | RERA registration number | Conditional
245 | City | 13 | Sub-division & Sale | C13.1 | Sub-division | Plot Sale | SAL-05 | Plot sub-division / individual patta | Yes
246 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-01 | Approved layout copy with LP number | Yes
247 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-04 | Parent title documents and latest EC | Yes
248 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-06 | Buyer KYC – PAN, Aadhaar, photographs | Yes
249 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-07 | Booking form and booking amount receipt | Yes
250 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-08 | Allotment letter | Yes
251 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-09 | Agreement for sale | Yes
252 | City | 13 | Sub-division & Sale | C13.2 | Marketing | Plot Sale | SAL-10 | Instalment payment receipts | Yes
253 | City | 13 | Sub-division & Sale | C13.3 | Sale Deeds | Plot Sale | SAL-11 | Bank NOC / loan sanction letter | Conditional
254 | City | 13 | Sub-division & Sale | C13.3 | Sale Deeds | Plot Sale | SAL-12 | TDS (1%) challan – Form 26QB | Conditional
255 | City | 13 | Sub-division & Sale | C13.3 | Sale Deeds | Plot Sale | SAL-13 | Stamp duty and registration fee payment | Yes
256 | City | 13 | Sub-division & Sale | C13.3 | Sale Deeds | Plot Sale | SAL-14 | Registered sale deed | Yes
257 | City | 13 | Sub-division & Sale | C13.3 | Sale Deeds | Plot Sale | SAL-15 | Possession / handover letter | Yes
258 | City | 13 | Sub-division & Sale | C13.4 | Patta Transfer | Plot Sale | SAL-16 | Patta transfer application / order | Yes

## Validation
Validation Checks
All checks must show OK before import.
# | Check | Result | Detail
1 | Instalment percentages total 100 | OK | Total = 100
2 | Last instalment due ≤ Sale Completion Window | OK | Last due = 13 working days, window = 15 days
3 | Percentage settings between 0 and 100 | OK | Out-of-range rows: 0
4 | All settings have a Unit Value | OK | Blank values: 0
5 | Setting Sino unique | OK
6 | Tenant Profile – required fields filled | ERROR | Missing required: 7
7 | Pin Code is 6 digits | ERROR | Value:
8 | Approval Task IDs unique | OK | Tasks: 148
9 | Approval durations are ≥ 0 | OK
10 | Facility IDs unique | OK | Facilities: 40
11 | Checklist Doc IDs unique | OK | Documents: 110
12 | Every applicable document mapped to a Task ID | OK
13 | Mapped Task IDs exist in Approval Stages | OK
14 | Every checklist has at least one item | OK
15 | Users – at least one Admin | ERROR | Admins: 0
16 | Users – rows complete (name, email, mobile, role) | ERROR | Users: 0
17 | Users – emails unique | OK
18 | Users – mobiles are 10 digits | OK
19 | Users – roles valid | OK
20 | Notification Groups – at least one active | OK
21 | Contact Number is 10 digits | ERROR | Value:
22 | Facility unit costs are > 0 | OK
| Overall status | FIX ERRORS

## Lists
Setting Type | Setting Unit | Area Type | Tier Flag | Yes/No | Checklist | Applies To | Mandatory | State | Role | Notification Type
App Settings | Code | Village | Y | Yes | Agri NOC | All | Yes | Tamil Nadu | Admin | Email
Instalment | Percentage | Town | - | No | DTCP Approval | Village | Conditional | Kerala | Manager
| Days | City | Opt |  | Local BDO Approval | Town | No | Karnataka | Sales
| Times |  |  |  | Town Approval | City |  | Andhra Pradesh | Accountant
[5 empty] | City Approval | Town, City |  | Telangana
[5 empty] | Gift Deed |  |  | Puducherry
RERA
Plot Sale